## Estimates - Comentarios
[5 empty] | Riesgo | 2
1st Stage | Administration App |  |  | Estimates | [6 empty] | Resources | 2
| Project (Incident) manager | [8 empty] | Hours | Days | Months
|  | Registrer a new project (incident) |  | 12 | 24 |  |  |  | STAGE 1 | 3376 | 211 | 10.55
|  | Quote Creation | [6 empty] | QA | 1350.4 | 63.3 | 12
|  |  | Checklist | 12 | 24 |  |  |  | PM | 675.2 | 6.33 | 12
|  |  | Template | 8 | 16 | Si es más de un template, esto puede subir considerablemente. Hay que a) Definir los diferentes templates b) Hacer un preview del template (una miniatura o descripción) c) Usar el template escogido. A como lo veo facil se podría llevar 7 días = 56 |  |  | Contingency | 675.2 | 42.2 | 2.11
|  |  | Categories | 8 | 16 |  |  |  | Totals | 6076.8 | 322.83 | 14
|  |  | Photos | 24 | 48
|  |  | Notes | 8 | 16 |  |  |  | El QA lo subiría al 40%, dado que es movil se puede complicar las pruebas en diferentes devices
| Xactimate Quote | [7 empty] | El PM lo pondría minimo un 20%, un 10% lo veo muy poco sobretodo porque hay varios "intermediarios" en el proceso. Y lo tomaría del tiempo total no solo de QA
|  | Connect Api |  | 24 | 48 |  |  |  | Acomodé la duración de otra forma. Yo pensaría que el QA y PM trabajen en paralelo, y un mes adicional para bugfixing y estabilización. Al final está quedando como un mes más corto.
|  | Generate Prices |  | 16 | 32
|  | Manual Rate |  | 24 | 48
|  | Genrate PDF |  | 12 | 24 |  |  |  | 48
|  | Send Email |  | 8 | 16 |  |  | Total | 291686.4
Visit tracker
|  | Sketches |  | 600 | 960 | Tendria que entender más contexto. Pero me imagino un canvas donde la persona que hace la visita tiene elementos que puede agragar al canvas, cambiar dimensiones y agregar comentarios. Lo veo como un trabajo de (a alto nivel) 2 personas por 3 meses = 960 horas +/- ver: https://roughjs.com/ | 960
|  | Events log |  | 56 | 112
| Timesheets |  |  |  |  | Ver: https://sheetjs.com/
|  | Equipment | Equipment Maintenance | 24 | 48
|  |  | Equipment Timesheet | 32 | 64
Reports
|  | Personnel |  |  | 0
|  |  | Timesheet | 16 | 32
|  |  | Reports |  | 0
| Administration | Categories Manintenance |  | 24 | 48
|  | Checklist maintenance |  | 60 | 120
|  | Templace maintenance |  | 30 | 60
|  | User Roles maintenance |  | 64 | 80 | Cuanto se puede compllicar un rol? Son roles unicamente del App? Si es lo tipico de apagar/encender features segun el rol unas 2 semanas deberia ser suficiente = 80 horas
| Framework | Login |  | 24 | 48 | Acá asumo que dependiendo del rol hay que apagar/mostrar features
Agregué esta tarea, que basicamente es tener una bd local en del device y un mecanismo (con ciertas reglas) para sincronizar cuando se vuelve a estar online
|  | General components |  | 52 | 104
|  |  | Total | 1138 | 1988
2nd Stage | Tablets | Registrer a new project (incident) |  | 12 | 24
Quote Creation
|  |  | Checklist | 12 | 24
|  |  | Template | 8 | 16
|  |  | Categories | 8 | 16
|  |  | Photos | 24 | 48
|  |  | Notes | 8 | 16
|  | Calculate route |  | 80 | 160
|  | See assignments |  | 32 | 64
|  | Sketches |  | 600 | 640 | 2 Recursos x 2 meses
|  | Measurement Feature |  | 160 | 320
|  | Push Notifications |  | 40 | 80
| Framework | Login |  | 8 | 16
|  | General components |  | 24 | 48
|  | Offiline db/sync |  | 320 | 60 | Lo bajé a 60 horas, no veo que sea tan complejo
|  |  | Total | 1336 | 1388

## Estimates
[5 empty] | Riesgo | 2
1st Stage | Administration App |  |  | Estimates |  |  |  |  | Resources | 2
| Project (Incident) manager | [6 empty] | Hours | Days | Months
|  | Registrer a new project (incident) |  | 12 | 24 |  | STAGE 1 | 2474 | 154.625 | 7.7313
|  | Quote Creation |  |  |  |  | QA | 742.2 | 46.3875 | 2.3194
|  |  | Checklist | 12 | 24 |  | PM | 74.22 | 4.6387 | 0.23194
|  |  | Template | 8 | 16 |  | Contingency | 494.8 | 30.925 | 1.5463
|  |  | Categories | 8 | 16 |  | Totals | 3785.22 | 236.5762 | 11.8288
|  |  | Photos | 24 | 48
|  |  | Notes | 8 | 16
Xactimate Quote
|  | Connect Api |  | 24 | 48
|  | Generate Prices |  | 16 | 32
|  | Manual Rate |  | 24 | 48
|  | Genrate PDF |  | 12 | 24
|  | Send Email |  | 8 | 16
Visit tracker
|  | Sketches |  | 600 | 1200
|  | Event mantanince |  | 56 | 112
Timesheets
|  | Equipment | Equipment Maintenance | 24 | 48
|  |  | Equipment Timesheet | 32 | 64
Reports
|  | Personnel |  |  | 0
|  |  | Timesheet | 16 | 32
|  |  | Reports |  | 0
| Administration | Categories Manintenance |  | 24 | 48
|  | Checklist maintenance |  | 60 | 120
|  | Templace maintenance |  | 30 | 60
|  | User Roles maintenance |  | 64 | 128
| Framework | Login |  | 24 | 48
|  | General components |  | 52 | 104
|  |  | Total | 1138 | 2276
2nd Stage | Tablets | Registrer a new project (incident) |  | 12 | 24
Quote Creation
|  |  | Checklist | 12 | 24
|  |  | Template | 8 | 16
|  |  | Categories | 8 | 16
|  |  | Photos | 24 | 48
|  |  | Notes | 8 | 16
|  | Calculate route |  | 80 | 160
|  | See assignments |  | 32 | 64
|  | Sketches |  | 600 | 1200
|  | Measurement Feature |  | 160 | 320
|  | Push Notifications |  | 40 | 80
| Framework | Login |  | 8 | 16
|  | General components |  | 24 | 48
|  | Offiline db/sync |  | 320 | 640
|  |  | Total | 1336 | 2528

## Features
https://www.nextgearsolutions.com/mica-mitigation-management-software/
| Web & Mobile support (offline) |  |  | https://www.youtube.com/watch?v=ZpqSQDRGpP8
| Incident manager |  |  | https://www.youtube.com/watch?v=zd1LTYG6M74
Registrer a new incident
By client
By agent
Incident tracking
Notes
Photos
Status
Document equipment Usage
|  | Bar code reader |  | https://codelabs.developers.google.com/codelabs/bar-codes/#0
Manual Tracking
Visit tracker
Request visit
Track visiit
Associate Incident
Register information
Photos
Psychometric & Mosture Data
Tracking projects
Projects
Reports
|  | Documents? | Visits
|  | Photos? | Metrics
|  | Sketch | Incidents
Quotes
Request a quote
|  | Quote work order | Automatic quote
Workflow (requested- reviewing - Approved)
Send quote
| Administration | Clients
Platform maintenance
Activate - Inactivate license
Usage report
2nd Stage | Pruvan | Manage Documents? |  | https://pruvan.com/
| (App for Employee to go to customers) | Schedule per day? | Shared or Print? | https://play.google.com/store/apps/details?id=com.pruvan.mobile3.direct&hl=en
|  | Get service request | Get survey's
|  | Calculate route | Payments? / Salaries?? / Apply Charges like purchases?
|  | Take photos / create quotes | Get notifications? about getting work or payments
3rd Stage | Pro Assits / Customer facing |  |  | https://www.youtube.com/watch?v=5X3YLV1KP8U
| (App for Customers to request services) | Request Service | Get notifications (when technician is assigned, arrived, completed) | https://www.nextgearsolutions.com/proassist-real-time-customer-connection/
|  | See historial? | Shared or Print?
|  | Get surveys to rate the service | Chat feature?
Sign documents (reader on mobile app)
Route tracking of the contractor
|  | Payments? | Notes

## Questions
Are you gonna proccess for payments? To technicians or get payments from customers?
After an order has been sent? can the technician do later changes or what happens when the review the quote and see something is missing
Are technicians or customers allowed to print copies or the drats or preorders? or just the approved ones?
Are the services urgent or do they need could schedule services for later days?
When do you need the development to be available? Are there any key milestones, important dates, or time constraints?
How many users are you expecting will use the apps?
Type of body compositions of the ends users for the tablet version?
Do you have an specific budget for the project?
Do you have any deadline fo the project?
Which are the key point to choose a vendor?

## Notes
Clients how use the application have an annual income of $1mill to more than $6.5mill | https://www.youtube.com/watch?v=BWRni6eR-KU.
Pruvan Pricing |  | Connect ~ Field Force
Connect ~ Back Office
Learning in the business: https://greggsargent.teachable.com/ | https://www.youtube.com/watch?v=Wmb7OD7Bbdo
https://www.itqlick.com/xactimate/pricing#:~:text=The%20price%20ranges%20are%20%2425,and%20%24150%20above%20per%20month.
Competitors
https://www.chetu.com/blogs/insurance/xactware-revolutionizes-exact-estimates.php
https://www.restorationmanager.net/mobile/
https://www.xactware.com/en-us/solutions/property-preservation/xactprm/landing-page-1/?SFCID=70130000000WxB2&LS=929
AP Integration - xactimate.com
https://github.com/Xactimate-One/sdk-php
https://xactimate.com/api/help
https://www.yumpu.com/en/document/view/38902667/xactimate-25-users-guidebook-xactware
https://www.xactware.com/store/PRODUCTS/Xactimate/Subscribe/Xactimate-Subscription/2-466.do

## Estimates (old)
[5 empty] | Riesgo | 2
1st Stage | Web & Mobile support (offline) |  |  | Estimates |  |  | Priority
| Incident manager | [7 empty] | Hours | Days | Months
|  | Registrer a new incident | [5 empty] | STAGE 1 | 1398 | 174.75 | 8.7375
|  |  | By client | 12 | 24 |  | 1 | STAGE 2 | 552 | 69 | 3.45
|  |  | By agent | 16 | 32 |  | 1 | STAGE 3 | 360 | 45 | 2.25
|  | Incident tracking |  |  | 0 |  |  | Totals | 2310 | 288.75 | 14.4375
|  |  | Notes | 24 | 48 |  | 1
|  |  | Photos | 28 | 56 |  | 1
|  |  | Status | 4 | 8 |  | 1 | 60
| Document equipment Usage |  |  | 7 | 14
|  | Bar code reader |  | 18 | 36 |  | 2
|  | Manual Tracking |  | 24 | 48 |  | 1
| Visit tracker |  |  |  | 0
|  | Request visit |  | 28 | 56 |  | 1
|  | Track visit |  | 22 | 44 |  | 1
|  | Associate Incident |  | 14 | 28 |  | 1
|  | Register information |  |  | 0 |  | 1
|  |  | Photos | 68 | 136 |  | 1 | Solo subir fotos, sino notas
|  |  | Psychometric & Mosture Data | 12 | 24 |  | 1
| Tracking projects |  |  |  | 0
|  | Projects |  | 16 | 32
|  | Reports |  |  | 0 |  |  | Mismia informacion, tracking
|  |  | Visits | 24 | 48 |  | 1 | No es una entidad aparte
|  |  | Metrics | 32 | 64 |  | 1
|  |  | Incidents | 24 | 48 |  | 1
| Quotes |  |  |  | 0
|  | Request a quote |  | 32 | 64
|  | Quote work order | Automatic quote | 32 | 64 |  |  | Solo generar documento
|  |  | Workflow (requested- reviewing - Approved) | 14 | 28 |  |  | Approve for review.
[5 empty] | 0 |  |  | Un solo documento para la aseguradora
|  | Send quote |  | 16 | 32
| Administration | Clients |  | 32 | 64 |  | 1
|  | Platform maintenance |  | 24 | 48 |  | 2
|  | Activate - Inactivate license |  | 8 | 16 |  | 2
|  | Usage report |  | 32 | 64 |  | 2
| Framework | Login |  | 32 | 64 |  | 1
|  | General components |  | 52 | 104 |  | 1
|  | Offiline db/sync |  | 52 | 104 |  |  | Para la desktop no hace falta
|  |  | Total | 699 | 1398
Do skectches
Handle Status
2nd Stage | Pruvan | Create a new incident |  |  |  |  | Se pueden crear casos
| (App for Employee to go to customers) | Schedule per day? (automatic?) |  | 80 | 160 |  | 1
|  | Get service request |  | 32 | 64
|  | Calculate route |  | 64 | 128 |  | 2
|  | Take photos / create quotes |  | 36 | 72 |  | 1 | no se ocupa crear quotes
|  | Shared or Print? |  | 0 | 0
|  | Get survey's |  | 0 | 0
|  | Payments? / Salaries?? / Apply Charges like purchases? |  | 0 | 0
|  | Get notifications? about getting work or payments |  | 8 | 16 |  | 1
| Framework | Login |  | 8 | 16 |  | 1
|  | General components |  | 24 | 48 |  | 1
|  | Offiline db/sync |  | 24 | 48 |  | 1
|  |  | Total | 276 | 552
3rd Stage | Pro Assits / Customer facing | [7 empty] | https://www.youtube.com/watch?v=5X3YLV1KP8U
| (App for Customers to request services) | Request Service |  | 6 | 12 |  | 3 |  | https://www.nextgearsolutions.com/proassist-real-time-customer-connection/
|  | See historial? |  | 12 | 24 |  | 3
|  | Get surveys to rate the service |  | 6 | 12 |  | 3
|  | Payments? |  | 24 | 48 |  | 3
|  | Get notifications (when technician is assigned, arrived, completed) |  | 8 | 16 |  | 3
|  | Shared or Print? |  | 4 | 8 |  | 3
|  | Chat feature? |  | 16 | 32 |  | 3
|  | Sign documents (reader on mobile app) |  | 16 | 32 |  | 3
|  | Route tracking of the contractor |  | 16 | 32 |  | 3
|  | Notes |  | 16 | 32 |  | 3
| Framework | Login |  | 8 | 16 |  | 3
|  | General components |  | 24 | 48 |  | 3
|  | Offiline db/sync |  | 24 | 48 |  | 3
|  |  | Total | 180 | 360

## Sheet1
Web App
| Based |  |  | Wks | Date | End
|  | Initial Setup | 40 | 2 | 2021-04-15 | 2021-04-29
|  | Set Dev Env | 10
| Administration |  |  | 4 | 2021-04-29 | 2021-05-27
|  | Users | 32 | 1
|  | Roles | 32 | 1
|  | Assign Roles to Users | 16 | 1
|  | Password | 36 | 1
Timesheet Module
|  | Settings | 24 | 2 | 2021-05-27 | 2021-06-10
| Security |  |  | 3 | 2021-06-10 | 2021-07-01
|  | Login | 16 | 1
|  | Reset Password | 16 | 1
|  | Forgot Password | 12 | 1
Reports
|  | Payment Report | 72 | 4 | 2021-07-01 | 2021-07-29
|  | Payroll Export | 54 | 4 | 2021-07-29 | 2021-08-26
iPad |  |  |  | Wks | Start | End
| Based |  |  | 3 | 2021-03-01 | 2021-03-22
|  | Initial Setup | 40
|  | Set Dev Env | 10
| Security |  |  | 3 | 2021-03-22 | 2021-04-12
|  | Login | 16 | 1
|  | Reset Password | 16 | 1
|  | Forgot Password | 12 | 1
| Settings |  |  | 1 | 2021-04-12 | 2021-04-19
|  | General | 8
| Timesheet |  |  | 8 | 2021-04-19 | 2021-06-14
|  | Daily Timesheet | 80 | 4
|  | Weekly Sign Off | 80 | 4
| Deploy to Prod |  | 24 | 2 | 2021-06-14 | 2021-06-28
|  | DEV | 646
|  | TEST | 193.8
|  | PM | 129.2
|  | TOTAL | 969
Formulas:
End = [Date]+(7*[Wks])
Date = [End, row above]